## Workplan 2022 to 2024
TRANSFORM HEALTH COALITION (THC) KENYA 2023 WORKPLAN
ACTIVITY | Organization responsible for delivery | Expected Output | INDICATOR |  | OUTCOMES | Actual Outcome (Both planned and unplanned outcomes can be listed here) | INDICATOR TARGET | Status | COLLABORATING PARTNERS | 2023
[10 empty] | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
|  |  |  | Purpose of Activity | [5 empty] | WK 1 | WK2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
Objective 1:Laws and policies on digital health technologies to achieve UHC commitments are developed and adopted at both national and county level by 2030 | THC Kenya | (i) E-Health Laws developed and enacted at county and national level; (ii) People-Centred digital health standards adopted | i) Number of Laws / policies developed and adopted; (ii) Number of Standards developed and adopted; (iii) Laws, policies and standard adopted that align with Transform Health Kenya's messaging |  | Enabling legal and policy environment at both national and county level |  | 1 national law;1 county law; 1 national standard |  | Ministry of Health, Kisumu County Government, Ministry of ICT
Sub - objective 1.1: Advocate for enactment of E-Health Laws in Kenya that advances the development, adoption and use of digital health technologies (to achieve UHC commitments. | THC Kenya | (i) E-Health Laws developed and enacted at county and national level; | (i) One E-Health law enacted at National Level; (ii) Number of E-Health laws enacted at county level |  | Enabling legal and policy environment at both national and county level |  | 1 national law;1 county law; |  | Ministry of Health, Kisumu County Government, Ministry of ICT
1.1.1: Develop a Human Rights Centered Legislative Guide of best practices adopted under international, regional and domestic legal frameworks; for use in advocacy | KELIN | (i) Legislative Guide Developed; (ii) Advocacy report | (i) No. of legislative guides published; (ii) No. of legislative guides disseminated to policy makers; (iii) No. of advocacy initiatives that are making use of the legislative guide | The aim of the legislative guide is to act as an advocacy tool for coalition members, young people, women, and vulnerable communities in advocating for the E-Health Law. The guide will be used in technical meetings with government as a summarized document containing proposals from the Coalition | Evidence generated for legal and policy change | Advocate for the enactment of the E- Health Act at National and County levels. | 1 legislative guide developed; 1 advocacy action plan developed; 500 copies of legislative guides disseminated | Legislative guide had been developed and validated by coalition members. Next steps involves design and dissemination to policy makers as well as coalition partners for use in advocacy | Coalition Partners, Ministry of Health, Kisumu County Government, Ministry of ICT
1.1.1.1 Undertake a Desk Research on the Best practices adopted under International, regional and domestic legal frameworks; and review the E-Health Bill 2020 | KELIN | (i) Draft Desk Report (ii) Draft legislative guide | No. of Desk Research Reports developed; No. of legislative guides developed | The desk research will analyse international best practices on digital health - and make recommendations on what the Kenyan digital health law should look like. The research report will be undertaken through both desk research, surveys and consultations with coalition partners. The findings will be used by partners in advocacy. | " | " | " | Desk Research Report developed and presented to coalition partners | bar: JANUARY WK2 to JANUARY WK 4
1.1.1.2 Validation Forum. (Validation to be conducted during the quarterly meeting) | KELIN | (i) Draft Desk Report (ii) Draft legislative guide | Validation Meeting Report | The validation meeting will be a platform for coalition members to validate the findings of the desk research and provide proposals to be included in the legislative guide | Increased knowledge on the legal framework around digital health technologies and best practise from the comparative analysis | Draft Legislative Guide validated by coalition members | 1 validation meeting of 20 coalition partners | bar: JANUARY WK 4
1.1.1.3 Dissemination of Legislative Guide Report: Dissemination of the legislative guide to policy makers during technical meetings with National and County Government | KELIN | Legislative guide , Report on the comparative research on digital health technologies and data | No. of dissemination meetings held; No. of people legislative guide disseminated to | To inform policy makers of the recommendations from the legislative guide and advocate for their adoption and inclusion in to the E-Health Bill | Enabling legal and policy environment at both national and county level | Legislative guide disseminated to policy makers to outline lessons learnt and opportunities for digital health in Kenya | 2 dissemination forums targeting policy makers; legislative guide disseminated to 50 policy makers; legislative guide dissemination to 500 health sector stakeholders including coaltion partners | bar: FEBRUARY WK 3
1.1.2: Champion for the enactment of a national E-Health Act through both technical assistance to government as well as mobilisation of communities to take part in public participation forums | KELIN | (i) Report of Technical Assistance to government; (ii) Report of support to communities to participate in public participation forums | (i) No. of technical meetings with government on the E-Health Bill; (ii) No. of consultative forums with communities; (iii)No. of community representatives actively taking part in public participation forums | This activity seeeks to secure commitment from policy makers to enact the E-Health Bill. The aim of the technical meetings will be to secure committment, and advocate for inclusion of recommendations from the coalition including youth, women and key populations | Enabling legal environment at the national level | '' | 3 Technical Meetings on E-Health Bill; 3 Community Dialogues on E-Health Bill; 10 Community representatives taking part in public participation on E-Health Bill | 1 technical meeting on the E-Health Bill conducted | Coalition Partners, Ministry of Health, Ministry of ICT, youth, women, and marginalised communities
1.1.2.1. Develop and publlish a Coalition Statement on the need for an E-Health Bill | KELIN | Statement/ article on the need for an E-health bill | (i) No or articles/statements; (ii) No. of people reached by statement; | The statement will be an advocacy tool that summarises the coalitions position on the importance of the bill and to advocate for timely passing of the bill into an act. | Enabling legal and policy environment at both national and county level | Evidenced information shared with medical practitioners, legislators, Ministry of Health, CSOs and other stakeholders on the need for an E-Health Act for Kenya | 1 statement supporting the need for an E-Health; 1 position statement with coalition's analysis of E-Health Bill; 3 articles in relation to the Bill
1.1.2.1 Connvene a technical meeting with Ministry of Health and Panel of Expers to review the latest draft of the E-Health Bill | KELIN | Meeting reports | (i) No of meetings held; (ii) No. of key policy makers taking part in the meetings | The aim of meeting will be to ensure recommendations from the coalition are included in the Bill and secure commitments on fast tracking the bill | increased advocacy for the passing a human rights centered E-Health Act | An E-Health Act draft is reviewed by experts to ensure that salient technical input is included | 1 technical meeting with 20 representatives of the Ministry of Health, coalition members and other experts | bar: FEBRUARY WK 3
1.1.2.2 Convene a Community Dialogue to sensitize young people, women, key populations and other community members on the E-Health Bill and document their recommendations | KELIN | Reports on Dialogue forum | (i) No. of community dialogues held; (ii) No. of community members sensitized on the bill; (iii) No. of statements containing recommendations from community members | To ensure that the community understands the provisions of the bill in anticipation of public participation. To ensure that the community's feedback is considered when reviewing the act. | increased knowledge on the features of the E-Health Bill and the ability for the community to express their views on it from an informed perspective and tom represent the views of the community | An E-Health Act with community and stakeholder input is drafted | 3 dialogue forums with 30 participants each; 1 joint statement containing community recommendations from the dialogues |  | WRA, Youth Alive Kenya, KP Consortium | bar: FEBRUARY WK 3
1.1.3. Champion for the development and enactment of a county-specific e-Health law in Kisumu County through technical assistance to the county government | KELIN | (i) Report of Technical Assistance to Kisumu County Government; | (i) No. of technical meetings with Kisumu County Government on a E-Health law; | The aim of this activity is to advocate for a county specific E-Health Law in Kisumu County. This will be through meetings to disseminate the legislative guide to Kisumu county and technical support in review of the Bill | Enabling legal environment for digital health at the county level | To ensure that digital health implementation is ' regulated in Kisumu County | 3 Technical meetings on a county e-Health law with 20 representatives of Kisumu County Government |  | Coalition Partners, Kisumu County Government
1.1.3.1 Advocacy engagement starting with a courtesy meeting with the Kisumu County Government on the uptake of digital health and the policy position on its implementation(in collaboration with Youth Alive) | KELIN | (i) Report of the Courtersy call meeting | (i) No. of meetings (ii) No. of policy makers engaged | To introduce the Coalition and its objectives to the county government and to discuss areas of collaboration and advocacy for the development of a county E-Health Bill | Increased understanding of the benefits of having a county E-Health Act | ' | 1 courtesy meeting held with top policy makers from Kisumu County Government on the need for a county e-health law. |  | Youth Alive, Men for Positive Living CBO, Pictures Youth Group, Nelson Mandela HIV&TB | bar: JANUARY WK 4
1.1.3.2 Inception meeting with the Kisumu County government officials to raise awareness and press for implementation of the County specific e-Health law | KELIN | (i) Report of the Inception meeting | (i) No. of meetings; (ii) No. of policy makers engaged in the meeting | To advance advocacy for the development of a county E-Health Bill and provide technical assistance to the county when drafting and disseminating the bill with stakeholders | Increased capacities and understanding of the benefits of having a county E-Health law, funding and implementation of the E-Health law | ' | 1 inception meeting with 30 Kisumu County Government representatives |  | Youth Alive, Men for Positive Living CBO, Pictures Youth Group, Nelson Mandela HIV&TB | bar: FEBRUARY WK 4
1.1.3.3. Meeting with County Government Officials to provide technical assistance to county government in the enactment of a county specific E-Health Bill | KELIN | (i) Report of the Technical Assistance meeting | (i) No. of meetings held; (ii) Commitments from county officials to develop the county e-Health Bill | To continue with talks and actions around developing a county E-Health Bill to guide the use of Digital health technologies | Enhanced use of the conty E-Health bill and continued dissemination of the bill and its importance in the promotion of UHC | ' | 2 meetings to provide technical assistance with representation from 20 county government representatives |  | Youth Alive, Men for Positive Living CBO, Pictures Youth Group, Nelson Mandela HIV&TB | bar: MAY WK 4
1.1.4. Identify and build capacity of women, youth, vulnerable and marginalized community champions to actively advocate for an enabling legal environment. | Youth Alive Kenya / WRA / Key Population Consortium | (i) Increased capacity of youth, women and KP champions to participate in law making processes | (i) No. of youth, women, and KP champions trained; (ii) No. of trained youth, women and KP champions actively participating in law making processes | To increase capacity of the KPs to navigate the legal environment leading to sustained work which is KP friendly. | Enhanced capacity of youth, women and Key Populations to advocate for an enabling legal environment at both national and county level | Well developed organizing amongst the KPs | 20 youth; 20 women and 20 KP champions trained and engaged as champions for digital health and rights |  | Coalition Partners
1.1.4.1 1 capacity-strengthening workshop on cultivating digital health champions in Nairobi | White Ribbon Alliance | Increased capacity of women digital health champions | No of women digital health champions trained and identified for further advocacy | to establish a community-based digital champion network trained on the digital health policy and legal environment, community organizing for digital health advocacy and budget advocacy processes and opportunities | Enhanced capacity of women to advocate for an enabling legal environment for digital health at both national and county level | Increased knowledge on digital health and its policy environment among young mothers, women with disabilities and women living in nomadic settings | 20 digital health community champions trained |  | WRA Kenya community champion network | bar: FEBRUARY WK 1 to FEBRUARY WK 4
Conduct a One (1) day project inception workshop for 30 identified key stakeholders (County government officials, CSO reps, and Media) and project staff in Kisumu . | Youth Alive! Kenya | Key project stakeholders understand project deliverables, roles, responsibilities, and expected outcomes of the project | # Of participants attending. # of govt officials in the inception meeting, # of project documents and visibility materials shared | to create a common understanding of the project deliverables with regard to youth before the start of the implementation | Increased understanding of project expected outcomes, roles, and responsibilities of all project stakeholders in the project. Initiate discussions on the development of a county E-Health bill in Kisumu County. Introduce the coalition to the County Government. Identify an advocacy engagement with CG of KSM; Directl involve the health committee, key focal officials for wider discussion. broader plan on E-health and follow up (support in drafting one, improving it, highlight the consortium’s position on the E-health). | Key stakeholders sensitized on the role of youth in the implementation of digital health technologies and data and youth inclusion in the process | Update report on the status of E-health bill in Kisumu CG. Broader plan on E-health and follow up; Clear engagement of the coalition; (support in drafting one, improving it, highlight the consortium’s position on the E-health). |  | county governemnt of Kisumu, County Government of Kisumu-CDOH, KP Consortium Youth Alive! Kenya project Staff Youth Advocates, Pictures YG, Nelson Mandela, YET4H. | bar: JANUARY WK 1 to JANUARY WK 4; FEBRUARY WK 2; MARCH WK 1 to MARCH WK 4; MAY WK 1 to MAY WK 4; JULY WK 1 to JULY WK 4; SEPTEMBER WK 1 to SEPTEMBER WK 4; NOVEMBER WK 1 to NOVEMBER WK 4
Bi-Monthly grassroots sensitization meetings with 25 youth leaders on Meaningful Youth Engagement to support mechanisms for soliciting and sharing information on advocacy strategies and plans | Youth Alive Kenya | Increased capacity of local youth leaders to develop advocacy strategies with decision-makers at the county level | # Of participants attending the session | to support mechanisms for soliciting and sharing information on advocacy strategies and plans | Local youth leaders have the capacity to support advocacy initiatives and meaningfully engage with policymakers | Youth leaders empowered to lead youth in advocacy for digital health | 25 youth leaders sensitized and engaged as champions for digita health |  | County Government of Kisumu, 25 budget champions, Nelson Mandela, Pictures YG. | bar: JANUARY WK 1 to JANUARY WK 4; MARCH WK 1 to MARCH WK 4; MAY WK 1 to JULY WK 4; SEPTEMBER WK 1 to SEPTEMBER WK 4; NOVEMBER WK 1 to NOVEMBER WK 4
Sensitization on E-Health Bill, Digital Health Technologies and Data Protection Act 2019 | Key Population Consortium | [i] Increased capacity of Key Populations to participate in the law making processes [ii] Enhanced capacity of Key Populations on importance of Digital Health Technologies. [iii] Acquisition of knowledge on how to advocacte for use and roll-out of the Digital Health Technologies. | (i)No. of KPs engaged during the sensitization meeting; (ii) No. of sensitization meetings held | To ensure that the KP are aware of the current laws that govern e-health technologies so that they use this knowledge to strengthen advocacy . To gain a legal perspective as they develop e-health platforms made specifically for Key populations | Enhanced capacity of KPs to advocate for an enabling legal environment at both national and county level | KPs being knowledgeable on the E-Health Bill and Digital Health Technologies and Data protection Act. | Sensitization of the 30 KP Champions from diverse KP-Led networks. |  | Key Population Champions Coailtion Partners | bar: MARCH WK 3
Sub-Objective 1.2: Advocate for people-centered digital health Standards and for standardization of digital health services and applications to achieve the goals of UHC. | THC Kenya | (i) People-centred digital health standards adopted | National Digital Health Standards Adopted |  | Enabling policy framework at national level |  | 1 national policy |  | Coalition partners
1.2.1 Conduct research to identify and analyze the existing digital health services and applications across the country and make recommendations on bests practices | PHDA | (i) Research Report identifying the exsting digital health services and applications | (i) No. of research reports published; (ii) No. of research reports disseminated; (iii) No. of advocacy initiatives that are making use of the research report | - | Evidence generated for legal and policy change | Knowledge on the framework upon which digital health technologies are operating, the number and types of application currently being used in health service delivery | 1 Research Report; 500 copies disseminated |  | Coalition partners; National & County Government State actors, private sector actors
1.2.1.1 Project planning and Research Protocol development | PHDA | Research protocol developed | no of research protocol | to ensure that the project implementation is well coordinated | enhanced clarity of the research topic to achieve the best outcomes | ' | 1 research protocol |  | ' | bar: JANUARY WK 3 to FEBRUARY WK 4
1.2.1.2 Data collection and cleaning | PHDA | data collection tools developed | no of data collection tools submitted | to ensure that the required data is collected and that it is relevant to the study. | evidence generated for quality analysis | ' | n/a |  | ' | bar: MARCH WK 1 to MARCH WK 4
1.2.1.3 Data analysis and report writing | PHDA | Research analysis conducted | no of reports on the data analysis developed | To tabulate the data into research findings and to report it | evidence generated to suit the targeted research needs | ' | 1 report developed |  | ' | bar: APRIL WK 1 to APRIL WK 4
1.2.1..4 Report Validation and project closeout | PHDA | research report validated | no of reports | To share the findings from the research for use in advocacy by stakeholders | enhanced knowledge on existing digital searvices and applications and the best practice. | ' | 1 report validation meeting |  | ' | bar: MAY WK 1 to MAY WK 4
1.2.2. Conduct research to analyse the standards and guidelines (national and/or international) that informed development and operation of existing digital health services and applications in the country and make recommendations on ideal standards | KEHIA | (i) Research Report on standards and guidelines | (i) No. of research reports published; (ii) No. of research reports disseminated; (iii) No. of advocacy initiatives that are making use of the research report | People centered digital health standards (developd) identified and adopted. To promote implementation of relevant digital health standards in digital health technologies | Evidence generated for legal and policy change | enhanced knowledge of the legal framework upon which digital health is operating. Identified gaps and needs in regulation of digital health | 1 Research Report ; 150 hard copies disseminated |  | Coalition partners, National & County Government State actors, private sector actors
1.2.3. Engage state actors and private sector actors in the national and county government on the need for people centered standardization of digital health technologies. | PHDA | (i) Enagement meeting reports utilising above research | (i) No. of meetings held; (ii) No of state actors and private sector actors engaged | to promote the standardization of digital health technologies to allow enhancement of the digital framework in Kenya | Enabling policy framework at national level | Enhanced knowledge and understanding of the gaps in the regulation and effective implementation of digital health technologies in Kenya | 30 state actors and 30 private sector actors engaged |  | Coalition partners, National & County Government State actors, private sector actors | bar: JANUARY WK 4 to MARCH WK 4
1.2.3.1 Project initiation and Development of shadow report informed by e health policy and concluded research recommendations. | PHDA | Shadow report | No of shadow reports | to plan the engagement with state actors targeted at dissemination of research findings | evidenced capacity building of state actors and opened avenues for evidence based advocacy | " | 1 shadow report developed |  | Coalition partners, National & County Government State actors, private sector actors | bar: JULY WK 1 to AUGUST WK 4
1.2.3.2 Engagement with State Actors, CSO’s & Private Stakeholders (County level) | PHDA | meeting reports | no of meetings held, no of reports | to enhance the knowledge of the county actors on the benefits of adopting apeople centred standardization of digital health technologies | evidenced and enhanced knowledge of County actors on the importanced of people centred standardization of digital health technologies | ' | 1 engagement with CSOs, I engagement with Private stakeholders, 1 engagement with state actors |  | Coalition partners, National & County Government State actors, private sector actors | bar: SEPTEMBER WK 1 to OCTOBER WK 4
1.2.3.3 Engagement with State Actors, CSO’s & Private Stakeholders (National Level) | PHDA | meeting reports | no of meetings held, no of reports | to enhance the knowledge of the state actors on the benefits of adopting apeople centred standardization of digital health technologies | evidenced and enhanced knowledge of state actors on the importanced of people centred standardization of digital health technologies | ' | 1 engagement with CSOs, I engagement with Private stakeholders, 1 engagement with state actors |  | Coalition partners, National & County Government State actors, private sector actors | bar: NOVEMBER WK 1 to NOVEMBER WK 4
Objective 2: Increased adoption and use of digital health technologies at the national and county government for access to equitable, affordable and quality health care; | THC Kenya | Digital health technologies adopted and used by both national and county governments | (i) No. of policy commitments to utilise digital health technologies implemented; (ii) No. of county governments making policy commitments to utilise digital technologies; (iv) No. of county governments implementing digital health policy commitments |  | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments |  | 1 national; 10 county governments |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
Sub-Objective 2.1. Advocate for implementation of national government policy commitments to adopt and use digital health technologies as well as for formulation of policy commitments at county level | THC Kenya | Digital health technologies adopted and used by both national and county governments | (i) No. of policy commitments to utilise digital health technologies implemented; (ii) No. of county governments making policy commitments to utilise digital technologies; (iv) No. of county governments implementing digital health policy commitments |  | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments |  | 1 national; 4 county governments policy commitments formulated / implemented |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.1. Identify government digital health champions (national and county health informatics officers) to champion policy formulation and implementation on adoption and use of digital health technologies | KEHIA | (i) Mapping and engagement meeting reports | (i) No. of government digital health champions identified; (ii) No. of engagements with the champions | To identify government officers who are working on digital health and are vital for advocacy for the development and implementation of digital health | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | Increased government led advocacy for digital health by official HRIOs | 20 champions from 4 counties; 1 advocacy and action planning forum with the champions; 3 follow up review meetings |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.1.1 Identify and map the government digital health champions National and county health records information officers (HRIOs) through the Council of Governors Health committee and the Ministry of Health’s ehealth technical working group’s membership roster | KEHIA | List of Government digital helth champions | Lists of HRIOs identified through the Council of Governors Health Committee and MOH E-health technical working group membership roster | to identify digital health champions and HRIOs who are already working with government to enhance advocacy initiatives | " | " | 1 list of HRIOs through the Council of Governors Health Committee and MOH E-health technical working group membership roster |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos) | bar: MAY WK 1 to MAY WK 4
2.1.1.2 Engage the selected HRIOs through email, webinars and in-person workshops and have discussions on how best digital health policies and solutions can be formulated, implemented and adopted by the Government. | KEHIA | Webinar reports and recordings on HRIO meetings | No of meeting reports | to ensure that the insider perspective on digital health and how to promote its implementation in government is considered in advocacy initiatives | " | " | 2 meeting reports |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos) | bar: JUNE WK 1 to JUNE WK 4
2.1.1.3 Facilitate discussions around mapping out policy gaps with regards to digital health and supporting the process of formulating / revision of the policies | KEHIA | Discussion reports on mapping out policy gaps on digital health | No of meeting reports on the discussions | to ensure they contain clear commitments on adoption and use of digital health technologies | " | " | 2 discussions/meetings on policy gaps |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos) | bar: JULY WK 1 to JULY WK 4
2.1.2. Support and facilitate roundtable dialogues with Ministry of Health Technical Working Groups (UHC & Health Informatics), Ministry of ICT, Media and Private Sector | KEHIA | (i) Roundtable dialogue reports | (i) No. of roundtable dialogues; (ii) No. of commitments formulated / implemented as a result of the dialogues | To ensure that all digital health stakeholders are able to discuss steps to promote the use of digital health technologies nationally and at county level | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | To ensure all stakeholders are part of the discussion on the promotion of digital health | 3 National Round Table; 3 forums per county in 4 counties; 15 State actors engaged at national level; 15 State actors engaged in each of the 4 counties |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.2.2 Engage the selected HRIOs through email, webinars and in-person workshops and have discussions on how best digital health policies and solutions can be formulated, implemented and adopted by the Government. | KEHIA | Webinar reports and recordings on HRIO meetings | (i) No. of meetings; (ii) No. of commitments formulated / implemented as a result of the dialogues | " | " |  | 4 National Round Table; 3 forums per county in 4 counties; 15 State actors engaged at national level; 15 State actors engaged in each of the 4 counties | bar: FEBRUARY WK 3 to MARCH WK 2
2.1.2.3 Organize in-person meetings/workshops and where necessary virtual webinars that will act as advocacy platforms on implementation of policy commitments, increased government leadership of digital health programmes, and as feedback mechanism platforms. | KEHIA | In person meeting reports | (i) No. of meetings; (ii) No. of commitments formulated / implemented as a result of the dialogues | " | " |  | 5 National Round Table; 3 forums per county in 4 counties; 15 State actors engaged at national level; 15 State actors engaged in each of the 4 counties | bar: MARCH WK 4; JUNE WK 4; SEPTEMBER WK 1
2.1.3. Host an annual multi-stakeholders conference during the Digital Health week as an accountability conference on the policy commitments | KELIN | (i) Conference report | (i) No. of conferences held; (ii) No. of commitments formulated / implemented as a result of the conference | - | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | Stakeholders discussed developments in the implementation of digital health technologies | 2 national conferences; 50 people participating |  | Ministry of Health, Ministry of ICT, 4 County Governments (UHC Pillot counties - Kisumu, Isiolo, Nyeri, Machakos)
2.1.3.1 Digital Health Week Conference. Conference preparation and execution. | KELIN | (i) Conference report | (i) No. of conferences held; (ii) No. of commitments formulated / implemented as a result of the conference | To have digital health stakeholders, service providers and government officials have a conversation on digital health and the progress on its implementation in Kenya as well as sharing best practise from other jurisdictions (symbolic gathering, not necessarily a conference) | " |  | '" | bar: OCTOBER WK 1 to OCTOBER WK 4
Sub-objective 2.2: Increase public demand for adoption and use of digital health technologies | THC Kenya | Increased public demand for adoption and use of digital health from youth, women, and key population groups | No. of public demands (Petitions, Letters, etc) from youth, women KP groups supporting the adoption of use of digital health technologies |  | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments |  | 1 national; 4 county governments policy commitments formulated / implemented |  | Coalition Partners, media, Ministry of Health, UHC pilot counties
2.2.1. Engage in media campaign to raise public awareness on fundamental role of digital health technologies in achieving UHC; and create demand for use and adoption on digital health technologies ; | Love Matters | (i) Media Campaign Strategy; (ii) Run 2 media campaigns (iii) Develop 2 comics (iv)Media Campaign Report | (i) No. of engagements generated from the media campaigns (ii) No. target audiences educated on UHC and the role of digital technologies in achieving it | Leverage on vibrant digital platforms to raise public awareness through information and education on UHC and digital technologies and ultimately create demand for the technologies | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | public sensitized on the fundamental role of digital health technologies in achieving UHC | 12 digital media activities developed and disseminated |  | Coalition Partners, Media, | bar: JANUARY WK 4; FEBRUARY WK 4; MARCH WK 4; APRIL WK 4; MAY WK 4; JUNE WK 4; JULY WK 4; AUGUST WK 4; SEPTEMBER WK 4; OCTOBER WK 4; NOVEMBER WK 4; DECEMBER WK 4
2.2.1.1 Create personas - Formulate hypothesis, Data collection, Putting a human face to data and Develop a comic to mirror the state of digital health in Kenya | Love Matters | Creation of a persona, Comic development, Access and download reports | Numbers of engagements on the posts i.e comments, shares, amplification by key partners | To ensure that the personas match the targeted demographic in order to create a meaningful comic that is easily understood by the community | Increased understanding of the state of digital health in Kenya | " | " |  | ' | bar: JANUARY WK2 to JANUARY WK 4
2.2.1.3 Production of video series to create awareness on UHC, digital technologies, and the linkage between the two | Love Matters | 5 videos created , accessed and downloaded | Numbers of engagements on the posts i.e comments,views, viewtime, shares, amplification by key partners | Increased understanding of UHC and how digital health technologies are contributing to it | Increased understanding of the linkage between UHC and Digital Health Teachnologies | " | " |  | ' | bar: FEBRUARY WK 1 to MARCH WK 1
2.2.1.4 Design and run campaign on digital health and rights | Love Matters | 1 media campaign on Digital Health Rights, Qualitative and quantitative media report | i) 1 media campaign created | to ensure that the community is informed about their rights when using digital health technologies | Increased understanding of digital health rights and access to digital health | " | " |  | ' | bar: JUNE WK 3 to SEPTEMBER WK 4
2.2.1.5 Develop a Comic around UHC | Love Matters | Comic On UHC | i) 1 comic created | to ensure that the community is informed about UHC and the steps Kenya is making to achieve it | enhanced knowledge on UHC and the steps taken by Kenya to achieve it | " | " |  | ' | bar: FEBRUARY WK 3 to MARCH WK 1; OCTOBER WK 1 to NOVEMBER WK 2
2.2.1.6 Design and Run Campaign on the role of digital health technologies in achieving UHC | Love Matters | Campaign strategy, Campaign report, qualitative and quantitative media report | i) 3 campaigns developed and run | To ensure that there is continuous information on digital health technologies and its connection to UHC | Increased knowledge on the role that digital health plays to achieve UHC | " | " |  | ' | bar: MARCH WK 4 to DECEMBER WK 3
2.2.2. Develop a community-led monitoring and accountability system and engage adolescents, youth, women and KP champions to, through use of score-cards, track commitments and assess the adoption and use of digital health systems | WRA / Youth Alive Kenya / Key Population Consortium | (i) Scorecard developed; (ii) Score card reports from youth, women and KP champions | (i) No. of scorecard developed; (ii) No. of community champions utilising the scorecards | To be able to track how health care service provision is and how best to improve the healthcare system. | Increased access to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | To be able to document the lived realities of KPs access to healthcare service provision as this will be the base of service delivery. | 30 youth, women and KP champions utilising the scorecard |  | Coalition Partners, Ministry of Health, County Governments
2.2.2.1 4 community dialogues in Bungoma, Kisumu, Narok, and Nairobi. Develop other actions that will contribute to the scorecard | White Ribbon Alliance | Community dialogue reports | No of community dialogue reports | To develop a matrix prioritizing the digital health needs and concerns of adolescent mothers, young women with disabilities, and women living in nomadic settings. To develop community action plans to conduct digital health advocacy at facility and county level | Enhanced knowledge on digital health rights to enable women to demand better health service delivery | Underserved women (young mothers, women with disabilitiesn and women living in nomadic settings) have increased confidence to self-express their digital health priorities Underserved women (young mothers, women with disabilities and women living in nomadic settings) have strengthened adocacy skills to take action for the digital health and UHC agenda | 100 community members participation in the community dialogue; 4 community dialogue reports and 4 community action plans |  | WRA Kenya champion network | bar: APRIL WK 1; APRIL WK 3 to MAY WK 1; MAY WK 3
2.2.2.2 4 community scorecard exercises Bungoma, Kisumu, Narok, and Nairobi | White Ribbon Alliance | Score cards Developed, Score card reports | No scorecards, No of score card reports | To complete scorecards demonstrating digital health interventions gaps and practices responsive to the health needs of adolescent mothers, young women with disabilities, and women living in nomadic settings | Increased understanding of digital health rights and the obligations of the county and national government in order to advocate for better service delivery in the county and nationally | Underserved women (young mothers, women with disabilities and women living in nomadic settings) have increased awareness of the state, and access, of digital health interventions in their local health facilities | 4 facility scorecards, 4 scorecard reports |  | WRA Kenya champion network, target health facilities county/sub-county level | bar: JUNE WK 1; JUNE WK 3 to JUNE WK 4; JULY WK 2; JULY WK 4
2.2.2.3. Development of an advocacy plan to prioritise on the Key Populations issues on use of digital health systems and a monitoring and accountablity system | Key Population Consortium | [i] Development of score cards and reports from Key Populations. [ii] Development of advocacy letters to the Ministries on how to engage with Key Populations in monitoring and accountability. | [i] No. of scorecards and reports developed; [ii] No. of Key Populations champions utilising the scorecards. (iii)No. of advocacy letters done. | To develop an advocacy plan targgeting key stakeholders on how to focus on use of digital health systems in different programs. | Increased access of Key Populations to equitable, affordable and quality health care as a result of increase in use of digital health technologies by national and county governments | Advocacy Strategies in place within KP organizing. | 1 Publication of advocacy strategies within KP organizations. |  | Key Population Champions Coailtion Partners | bar: JULY WK 3
2.2.2.4 Facilitate quarterly accountability forums by the coalition | Youth Alive Kenya | Scorecard tools, and reports developed through engagements with the Kisumu County government | # Of scorecard tools and reports developed; # of community champions utilizing the scorecards | To discuss progress made by the Kisumu County governments towards meeting gender equality and SRHR needs , integrating digital health technologies and to make proposals to the County Assembly (CA) where there are gaps identified | increased accountability on allocation and utilization of county funds towards promoting universal health care and use of digital health in Kisumu County | Implementation tracking, advocacy for the use of digital health and implementation of UHC | 4 scorecards developed, 4 county engagement reports developed |  | County Government, coalition memebers, digital health and budget champions | bar: APRIL WK 3; AUGUST WK 3; NOVEMBER WK 3
3. Increased resources at national and county level for strengthening digital health technologies to achieve UHC commitments | THC Kenya | Increased resources for digital health at national and county level | Amount of resouces allocated to digital health at national and county level |  | Increased resources at national and county level for strengthening digital health technologies to achieve UHC commitments |  | Increased national resources; Increased resources in four UHC pilot counties |  | Coalition Partners, Ministry of Health, County Governments
Sub-Objective 3.1. Generate evidence and advocate for the inclusion of digital health technologies in the budget allocations | THC Kenya | Evidence generated for advocacy to increase resources for digital health | Amount of resouces allocated to digital health at national and county level |  | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments |  | Increased national resources; Increased resources in four UHC pilot counties |  | Coalition Partners, Ministry of Health, County Governments
3.1.1. Conduct a resource gap analysis to identify the resources required to achieve efficient use and adoption of digital health technologies. | KEHIA | (i) Resource Gap Analysis Report | (i) No. of research reports published; (ii) No. of research reports disseminated; (iii) No. of advocacy initiatives that are making use of the research report | To identify the resources required including funding gaps to promote the adoption and rightful use of digital health technologies and advocate for their allocation by government | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | Resource gap for digital health identified | 1 Research Report ; 500 copies disseminated |  | Coalition Partners, Ministry of Health, County Governments | bar: JANUARY WK 3 to FEBRUARY WK 2
3.1.2. Engage national and county government officials using the evidence generated above on the inclusion of digital health technologies in budget allocations. | KEHIA | (i) Engagement meeting reports | No. of engagements with national and county government officials | To disseminate the research findings on the resource gap on the budgetary inclusion of digital health in counties and nationally (ensure the analysis is thorough) | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | Officials sensitized on the importance of having an allocation for digital health in the budget | 2 national engagements; 2 county engagements in each of the 4 pilot counties |  | Coalition Partners, Ministry of Health, County Governments
3.1.3:Enhance capacity and support youth, women, vulnerable and marginalized groups champions to engage in budget making processes and advocate for prioritization of resources for digital health technologies | Youth Alive Kenya/ WRA / Key Population Consortium | [i] Capacity building report; [ii] Report of support provided | No. of youth, women, KP groups actively engaging in budget making processes | To familiarize youth women and key populations with budget monitoring and influencing skills to enable them influence and monitor allocation for digital health technologies | Increased resources at national and county levels prioritizing funding for digital health technologies with youth, women and marginalized communities as key beneficiaries. | Women , youth and key populations acquire develop skills in budget making, tracking and advocacy | 30 youth, women, KP champions actively engaging in budget making processes |  | Coalition Partners, Ministry of Health, County Governments | bar: DECEMBER WK 1
3.1.3.1. Support digital health champions to participate in 4 public meetings being convened by County Assembly Budget and Approriations Committee in Bungoma, Kisumu, Narok, and Nairobi | White Ribbon Alliance | meeting reports | No. of meetings, No of reports | To enable community champions to present community-generated demands in public participation and advocacy forums across the budget cycle | Trained digital health champions are more familiar with county budget review meetings and have increased confidence to participate and drive the digital health agenda | " | 20 women champions attend at least 4 budget public hearings; 4 county meeting minutes |  | WRA Kenya champion network, County Governments | bar: APRIL WK 1 to APRIL WK 4
3.1.3.2. 4 community conversations in Bungoma, Kisumu, Narok, and Nairobi to review the Annual Development plan and ensure it reflects and provides for community needs and priorities | White Ribbon Alliance | meeting reports | No. of meetings, No of reports | to ignite a community-led advocacy and accountability champion network advocate for an inclusive digital health legal framework to ensure digital health is mainstreamed in health policies, programs and practice at county, facility and community levels | Underserved women (young mothers, women with disabilitiesn and women living in nomadic settings) have increased knowledge of the county annual development plans and are able to map community priorities on digital health needs | " | At least 100 community members (women) are actively engaged in community conversations; 4 county session reports |  | WRA Kenya champion network, County Governments | bar: SEPTEMBER WK 1 to SEPTEMBER WK 4
3.1.3.3. Conduct a 3 days training for 30 youth budget champions and coalition members on county planning and budgeting processes with a special focus on public participation in E-Health Laws in Kenya and the use of digital health technologies to achieve UHC commitments; | Youth Alive | increased awareness on the E-health bill, data protection act, and budget advocacy | # of advocacy initiatives, engagements, or issues raised by budget champions relating to digital health technologies # of budget champions trained # of advocacy actions on digital health and county budgeting actions prioritized. | To enhance the skills and understanding of participants on how to approach youth issues in public participation and in the budget making process | Increased allocation of resources supporting digital health platforms and technologies in health service delivery for Kisumu County | " | 30 youth budget champions and coalition members are trained on county planning and budget processes |  | Youth Leaders, Kisumu CDOH-Officials, YAK Project Staff | bar: APRIL WK 2
3.1.3.4. Engaging in the budget making process and advocating for prioritization of resources for digital health technologies | Key Population Consortium | [i] Capacity building report; [ii] Report of support provided | No. of youth, women, KP groups actively engaging in budget making processes | To enhance the skills and understanding of participants in the budget making process | Increased resources at national and county levels for strengthening digital health technologies to achieve UHC commitments | KPs knowing on how to engage in the budget making processes leading to funded KP organizations | Sustained KP organizations having well funded programmes. |  | Key Population Champions Coailtion Partners | bar: DECEMBER WK 1
4. COALITION GOVERNANCE, GROWTH & DEVELOPMENT
4.1. Identify and invite new members to the coalition | Program Officer Health & Governance | Commitment letters signed | No. of new members | To build a movement for the advocacy of digital health technologies in Kenya and to ensure that there contributory expertise is vast | Growth of coalition | Transform Health Kenya Coalition Members increased | 10 per year | 23 current members | Coalition partners | bar: JANUARY WK 3 to MARCH WK 1; MARCH WK 3 to APRIL WK 2; APRIL WK 4 to MAY WK 3; JUNE WK 1 to JUNE WK 3; JULY WK 1 to SEPTEMBER WK 3; OCTOBER WK 1 to DECEMBER WK 4
4.2. Conduct annual capacity building of coalition members on emerging issues with regards to digitial health technologies and UHC | Program Officer Health & Governance | Training meeting report | No. of coalition members trained; Increase in knowledge | To ensure that the coalition members are kept up tp date with critical information and skills with regard to digital health | Increase in knowledge of coalition partners on emerging issues | Enhanced capacities of coalition members on emerging issues around digital health | 2 trainings conducted; 20 members trained | 4 capacity building sessions | Coalition partners | bar: FEBRUARY WK 4; APRIL WK 4
4.3 Conduct Quarterly Meetings of the Coalition to review progress in implementation of strategy and plan for upcoming interventions | Program Officer Health & Governance | Reviewmeeting reports | No. of coalition members taking part in the meetings; Progress report of activities | To review progress of implementation of the coalition workplan and to identify new areas of advocacy and coordination among the coalition members | Coordinated implementation of activities | Enhanced synergy among coalition members to implement the project | 4 review meetings per year; 20 members taking part in each meeting | 4 meeting held | Coalition partners | bar: JANUARY WK 4; MAY WK 3; SEPTEMBER WK 4
4.4. Develop a website and social media platforms for Transform Health Kenya Coalition | Program Manager Health & Governance | Website and social media platforms | Website and social media engagement reports | To showcase the work that the coalition is doing to advance the use of digital health technologies in Kenya | Wider reach of Transform Health advocacy messages and updates on the coalition's activities and campaigns | partners are informed of opportunities for partnership. Partners are educated on the coal;ition's initiatives | messaging reaching 1 million people | 1 website developed and 2 social media pages opened and populated with information on the coalition's work | Coalition partners
4.5. Joint Fundraising for the coalitions activities and advocacy interventions | KELIN, TH Kenya Resource Mobilisation Committee & Transform Health | - At least find funding partners identified and approached; - At least three funding proposals developed and submitted between 2023 and 2024 | No of funding partners identified No of funding proposals submitted Amount of resources fundraised | To ensure that the Coalition continuously sources for funds to enhance the coalition's advocacy work on digital health technologies | Coalition growth, sustainability and development | 2 proposals submitted to Commonwealth Fund | - TH Kenya raises $368,469 to cover 50% of coalition expenses in 2023 and 2024. | 4 proposals submitted | Coalition Partners Fund raising committee | bar: FEBRUARY WK 4; MARCH WK 4; APRIL WK 4; MAY WK 4; JUNE WK 4; JULY WK 4

## Sheet5
TRANSFORM HEALTH COMMENTS
TRANSFORM HEALTH NATIONAL COORDINATING PARTNER-KENYA
| PROPOSAL BUDGET FOR 6 MONTHS | No. | Unit Cost | Frequency | Unit of Frequency | Total (Kshs) | Total (USD)
Activity 1. Establish the national coalition platform with initial 20 member organization
1.1: | Conduct a meeting of the national project steering committee to disseminate the findings of the initial landscape analysis and discuss roll out of expanded research on digital health
| Full day conference package @ 4,000 * 20 pax | 20 | 4000 | 1 |  | 80000 | 800
| Honorarium for facilitator @ Ksh 10,000 | 1 | 10000 | 1 |  | 10000 | 100
| Rapportuer @ 10,000/= per day | 1 | 10000 | 1 |  | 10000 | 100
| Transport reimbursement for participants - 17 pax @ 2,000 | 17 | 2000 | 1 |  | 34000 | 340
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 1 |  | 20000 | 200
| Coordination transport for staff | 1 | 7000 | 1 |  | 7000 | 70
| Subtotal |  |  |  |  | 161000 | 1610
1.2: | Undertake indepth research on equitable access to digital health technologies and universal health coverage in Kenya
1.2.1 | Develop Terms of Reference and recruit consultant for the research
| Engage consultant in conducting research | 1 | 30000 | 33 | days? | 990000 | 9900 | what is the 33 unit number of days? - This is the estimated number of days the consult
| Subtotal |  |  |  |  | 990000 | 9900
1.2.2 | Facilitate the consultant to conduct focus group discussions and data collection from both urban, peri urban and rural counties
Logistics
| Accommodation and meals for consultants and staff | 5 | 12000 | 12 | days? | 720000 | 7200
| Material cost & mobilization | 1 | 30000 | 6 |  | 180000 | 1800
| Hall hire for FGD | 1 | 10000 | 6 |  | 60000 | 600
| Refreshments | 25 | 500 | 6 |  | 75000 | 750
| Transport reimbursements | 25 | 1000 | 6 |  | 150000 | 1500
| Return air travel for 5 pax | 5 | 20000 | 4 |  | 400000 | 4000 | Where will people be flying to - please state locations and share links for costs
| Coordination transport and transfers | 1 | 30000 | 6 |  | 180000 | 1800
Virtual FGD
| Data reimbursements for participants | 25 | 1000 | 6 |  | 150000 | 1500 | Please add in what the purpose of data reimbursments are
| Sub-total |  |  |  |  | 1915000 | 19150
1.2.3 | Conduct a meeting of the national project steering committee to validate the findings of the research
| Data reimbursements | 25 | 2000 | 1 |  | 50000 | 500 | Please add in what the purpose of data reimbursments are
| Mobilization costs | 1 | 5000 | 1 |  | 5000 | 50 | Please add what these moblisation costs pay for?
| Subtotal |  |  |  |  | 55000 | 550
1.3 | Launch National Campaign during Digital Health Week
1.3.1 | Conduct Social Media validation of the issues documented from the research findings
| Staff time | 1 | 0 | 0 |  | 0 | 0
| Sub total |  |  |  |  | 0 | 0
1.3.2 | Disseminate the findings of the research on mainstream media (TV / radio talk shows )
| Main media | 1 | 500000 | 1 |  | 500000 | 5000 | What will this pay for please add in detials in column B
| Sub total |  |  |  |  | 500000 | 5000
1.3.3 | Conduct a national conference with various actors in the digital health and UHC space in Kenya to disseminate the findings of the research and to officially launch the Transform Health Coalition in Kenya
| Accommodation and meals for participants from out of town | 10 | 12000 | 2 |  | 240000 | 2400
| Conference package for 35 pax @ 4,000 pp for one day | 35 | 4000 | 1 |  | 140000 | 1400
| Honorarium for facilitator @ Ksh 10,000 | 3 | 10000 | 1 |  | 30000 | 300
| Rapportuer Fee @ 20,000/= per day | 1 | 20000 | 1 |  | 20000 | 200
| Transport reimbursement for participants in Nairobi county | 25 | 2000 | 1 |  | 50000 | 500
| Transport reimbursement for participants out of Nairobi county | 5 | 5000 | 1 |  | 25000 | 250
| Air transport for 5 participants | 5 | 20000 | 1 |  | 100000 | 1000
| Transfers and coordination | 1 | 25000 | 1 |  | 25000 | 250
| Design of banners/report | 1 | 20000 | 5 |  | 100000 | 1000
| Meeting material (mobilization, PPEs etc) | 1 | 25000 | 1 |  | 25000 | 250
| Printing of materials for launch | 200 | 900 | 1 |  | 180000 | 1800
| Sub total |  |  |  |  | 935000 | 9350
1.4 | Establish the Transform Health National Coalition
1.4.1 | Invite 20 members to join the Transform Health Coalition
| Staff time | 1 | 0 | 0 |  | 0 | 0
| Sub total |  |  |  |  | 0 | 0
[6 empty] | 0 | 0
1.4.2. | Conduct a two-day introductory meeting and training to introduce Transform Health; develop a Memorandum of Understanding; and develop a shared understanding of UHC in the digital age |  |  |  |  | 0 | 0 | 1.4.2 and 1.5 should be collapsed into a single event 4 days
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 |  | 200000 | 2000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 40000 | 1 |  | 40000 | 400
| Transport reimbursements to participants | 20 | 2000 | 1 |  | 40000 | 400
| Honorarium | 3 | 10000 | 2 |  | 60000 | 600
| Coordination transport for staff | 1 | 7000 | 2 |  | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 |  | 60000 | 600
| Rapporteur | 1 | 50000 | 1 |  | 50000 | 500
[6 empty] | 0 | 0
[6 empty] | 464000 | 4640
1.5 | Conduct a two -day workshop of Coalition partners to brainstorm and develop the a work plan, Theory of Change and national campaign and influencing strategy for the National Coalition
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 |  | 200000 | 2000
| Accomodation and meals for 25 pax | 25 | 12000 | 3 |  | 900000 | 9000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 30000 | 1 |  | 30000 | 300
| Transport reimbursements to participants | 17 | 2000 | 2 |  | 68000 | 680
| Coordination transport for staff | 1 | 7000 | 2 |  | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 |  | 60000 | 600
| Rapporteur | 1 | 50000 | 1 |  | 50000 | 500
[6 empty] | 0 | 0
[6 empty] | 1322000 | 13220
1.5.1 | Develop Terms of Reference and recruit consultant for the Theory of Change
| Engage a consultant | 1 | 30000 | 9 |  | 270000 | 2700 | This should be conducted in house. Transform Health can facilitate
| Sub total |  |  |  |  | 270000 | 2700
1.5.2 | Conduct a meeting of the national steering committee to validate the Theory of Change
| Data reimbursements | 25 | 2000 | 1 |  | 50000 | 500 | Please add in what the purpose of data reimbursments are
| Mobilization | 1 | 5000 | 1 |  | 5000 | 50 | Please add what these moblisation costs pay for?
| Subtotal |  |  |  |  | 55000 | 550
1.5.3. | Develop Terms of Reference for a consultant for work plan development and for communications & campaign strategy
| Engage a consultant | 1 | 30000 | 9 |  | 270000 | 2700 | This should be conducted in house. Transform Health can facilitate
| Sub total |  |  |  |  | 270000 | 2700
1.5.4. | Conduct meeeting of the national steering committee to validate the work plan and campaign strategy
| Data reimbursements | 25 | 2000 | 1 |  | 50000 | 500 | Please add in what the purpose of data reimbursments are?
| Mobilization | 1 | 5000 | 1 |  | 5000 | 50 | What cost is this in relation to mobilisation - state details in column B?
| Subtotal |  |  |  |  | 55000 | 550
| Project Activities Total |  |  |  |  | 6992000 | 69920
Contribution To Project Staff Salaries
| Program Manager Health & Governance % of staff time per month | 1 | 128000 | 3 | months | 384000 | 3840 | What is the actual % please state in column B for each staff member
| Program Officer Health & Governance % of staff time per month | 1 | 120000 | 3 | months | 360000 | 3600 | What is the actual % please state in column B for each staff member
| DED % of staff time per month | 1 | 80000 | 3 | months | 240000 | 2400 | What is the actual % please state in column B for each staff member
| Executive Director % of staff time per month | 1 | 50000 | 3 | months | 150000 | 1500 | What is the actual % please state in column B for each staff member
| M & E advisor % of staff time per month | 1 | 75000 | 3 | months | 225000 | 2250 | What is the actual % please state in column B for each staff member
| Finance & Administration Manager % of staff time per month | 1 | 90000 | 3 | months | 270000 | 2700 | What is the actual % please state in column B for each staff member
| Communications Officer % of staff time per month | 1 | 75000 | 3 | months | 225000 | 2250 | What is the actual % please state in column B for each staff member
| Sub total |  |  |  |  | 1854000 | 18540 | Staff and Overhead costs are 30% of total costs - by donor standards this is too high - should be around 15 to 20%
General Office Administration Costs
| Utilities, Internet Costs @ 250,000 per month | 1 | 341666.67 | 3 |  | 1025000.01 | 10250.0001
| Sub total |  |  |  |  | 1025000.01 | 10250.0001
| Total budget |  |  |  |  | 9871000.01 | 98710.0001
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ====== ID#AAAAPhasqtE Frank Smith (2021-09-28 09:58:19) This should be covered in the landscape analysis and may not be necessary during this phase. Consider including this in the next plan
Note on B53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ====== ID#AAAAPhasqtI Frank Smith (2021-09-28 10:00:03) Here is where we want to launch the landscape analysis as a report with strong recommendations.

## TAB 2 Budget (hidden)
TRANSFORM HEALTH COMMENTS
TRANSFORM HEALTH NATIONAL COORDINATING PARTNER-KENYA
| PROPOSAL BUDGET FOR 6 MONTHS | No. | Unit Cost | Frequency | Total (Kshs) | Total (USD)
Activity 1. Establish the national coalition platform with initial 20 member organization
1.1: | Conduct a meeting of the national project steering committee to disseminate the findings of the initial landscape analysis and discuss roll out of expanded research on digital health
| Full day conference package @ 4,000 * 20 pax | 20 | 4000 | 1 | 80000 | 800
| Honorarium for facilitator @ Ksh 10,000 | 1 | 10000 | 1 | 10000 | 100
| Rapportuer @ 10,000/= per day | 1 | 10000 | 1 | 10000 | 100
| Transport reimbursement for participants - 17 pax @ 2,000 | 17 | 2000 | 1 | 34000 | 340
| Meeting material (mobilization, printing, photocopying, PPEs etc) | 1 | 20000 | 1 | 20000 | 200
| Coordination transport for staff | 1 | 7000 | 1 | 7000 | 70
| Subtotal |  |  |  | 161000 | 1610
1.2: | Undertake indepth research on equitable access to digital health technologies and universal health coverage in Kenya
1.2.1 | Develop Terms of Reference and recruit consultant for the research
| Engage consultant in conducting research | 1 | 30000 | 33 | 990000 | 9900
| Subtotal |  |  |  | 990000 | 9900
1.2.2 | Facilitate the consultant to conduct focus group discussions and data collection from both urban, peri urban and rural counties
Logistics
| Accommodation and meals for consultants and staff | 5 | 12000 | 12 | 720000 | 7200
| Material cost & mobilization | 1 | 30000 | 6 | 180000 | 1800
| Hall hire for FGD | 1 | 10000 | 6 | 60000 | 600
| Refreshments | 25 | 500 | 6 | 75000 | 750
| Transport reimbursements | 25 | 1000 | 6 | 150000 | 1500
| Return air travel for 5 pax | 5 | 20000 | 4 | 400000 | 4000
| Coordination transport and transfers | 1 | 30000 | 6 | 180000 | 1800
Virtual FGD
| Data reimbursements for participants | 25 | 1000 | 6 | 150000 | 1500
| Sub-total |  |  |  | 1915000 | 19150
1.2.3 | Conduct a meeting of the national project steering committee to validate the findings of the research
| Data reimbursements | 25 | 2000 | 1 | 50000 | 500
| Mobilization costs | 1 | 5000 | 1 | 5000 | 50
| Subtotal |  |  |  | 55000 | 550
1.3 | Launch National Campaign during Digital Health Week
1.3.1 | Conduct Social Media validation of the issues documented from the research findings
| Staff time | 1 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 | 0
1.3.2 | Disseminate the findings of the research on mainstream media (TV / radio talk shows )
| Main media | 1 | 500000 | 1 | 500000 | 5000
| Sub total |  |  |  | 500000 | 5000
1.3.3 | Conduct a national conference with various actors in the digital health and UHC space in Kenya to disseminate the findings of the research and to officially launch the Transform Health Coalition in Kenya
| Accommodation and meals for participants from out of town | 10 | 12000 | 2 | 240000 | 2400
| Conference package for 35 pax @ 4,000 pp for one day | 35 | 4000 | 1 | 140000 | 1400
| Honorarium for facilitator @ Ksh 10,000 | 3 | 10000 | 1 | 30000 | 300
| Rapportuer Fee @ 20,000/= per day | 1 | 20000 | 1 | 20000 | 200
| Transport reimbursement for participants in Nairobi county | 25 | 2000 | 1 | 50000 | 500
| Transport reimbursement for participants out of Nairobi county | 5 | 5000 | 1 | 25000 | 250
| Air transport for 5 participants | 5 | 20000 | 1 | 100000 | 1000
| Transfers and coordination | 1 | 25000 | 1 | 25000 | 250
| Design of banners/report | 1 | 20000 | 5 | 100000 | 1000
| Meeting material (mobilization, PPEs etc) | 1 | 25000 | 1 | 25000 | 250
| Printing of materials for launch | 200 | 900 | 1 | 180000 | 1800
| Sub total |  |  |  | 935000 | 9350
1.4 | Establish the Transform Health National Coalition
1.4.1 | Invite 20 members to join the Transform Health Coalition
| Staff time | 1 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 | 0
[5 empty] | 0 | 0
1.4.2. | Conduct a two-day introductory meeting and training to introduce Transform Health; develop a Memorandum of Understanding; and develop a shared understanding of UHC in the digital age |  |  |  | 0 | 0
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 | 200000 | 2000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 40000 | 1 | 40000 | 400
| Transport reimbursements to participants | 20 | 2000 | 1 | 40000 | 400
| Honorarium | 3 | 10000 | 2 | 60000 | 600
| Coordination transport for staff | 1 | 7000 | 2 | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 | 60000 | 600
| Rapporteur | 1 | 50000 | 1 | 50000 | 500
[5 empty] | 0 | 0
[5 empty] | 464000 | 4640
1.5 | Conduct a two -day workshop of Coalition partners to brainstorm and develop the a work plan, Theory of Change and national campaign and influencing strategy for the National Coalition
| Conference costs for 25 pax @ 4,000 pp for 1 day | 25 | 4000 | 2 | 200000 | 2000
| Accomodation and meals for 25 pax | 25 | 12000 | 3 | 900000 | 9000
| Material costs (printing, photocopying, mobilization, PPEs etc) | 1 | 30000 | 1 | 30000 | 300
| Transport reimbursements to participants | 17 | 2000 | 2 | 68000 | 680
| Coordination transport for staff | 1 | 7000 | 2 | 14000 | 140
| Facilitation honorarium | 3 | 10000 | 2 | 60000 | 600
| Rapporteur | 1 | 50000 | 1 | 50000 | 500
[5 empty] | 0 | 0
[5 empty] | 1322000 | 13220
1.5.1 | Develop Terms of Reference and recruit consultant for the Theory of Change
| Engage a consultant | 1 | 30000 | 9 | 270000 | 2700
| Sub total |  |  |  | 270000 | 2700
1.5.2 | Conduct a meeting of the national steering committee to validate the Theory of Change
| Data reimbursements | 25 | 2000 | 1 | 50000 | 500
| Mobilization | 1 | 5000 | 1 | 5000 | 50
| Subtotal |  |  |  | 55000 | 550
1.5.3. | Develop Terms of Reference for a consultant for work plan development and for communications & campaign strategy
| Engage a consultant | 1 | 30000 | 9 | 270000 | 2700
| Sub total |  |  |  | 270000 | 2700
1.5.4. | Conduct meeeting of the national steering committee to validate the work plan and campaign strategy
| Data reimbursements | 25 | 2000 | 1 | 50000 | 500
| Mobilization | 1 | 5000 | 1 | 5000 | 50
| Subtotal |  |  |  | 55000 | 550
| Project Activities Total |  |  |  | 6992000 | 69920
Contribution To Project Staff Salaries
| Program Manager Health & Governance % of staff time per month | 1 | 128000 | 6 | 768000 | 7680
| Program Officer Health & Governance % of staff time per month | 1 | 120000 | 6 | 720000 | 7200
| DED % of staff time per month | 1 | 80000 | 6 | 480000 | 4800
| Executive Director % of staff time per month | 1 | 50000 | 6 | 300000 | 3000
| M & E advisor % of staff time per month | 1 | 75000 | 6 | 450000 | 4500
| Finance & Administration Manager % of staff time per month | 1 | 90000 | 6 | 540000 | 5400
| Communications Officer % of staff time per month | 1 | 75000 | 6 | 450000 | 4500
| Sub total |  |  |  | 3708000 | 37080
General Office Administration Costs
| Utilities, Internet Costs @ 250,000 per month | 1 | 341666.67 | 6 | 2050000.02 | 20500.0002
| Sub total |  |  |  | 2050000.02 | 20500.0002
| Total budget |  |  |  | 12750000.02 | 127500.0002

## Sheet1
MONITORING & EVALUATION FRAMEWORK 6 months
STRATEGY & ACTIVITY | OUTPUT | OUTCOME | IMPACT
|  |  |  | Impact Indicators | Indicator | NC - Kenya
|  |  |  | Outcome Indicators | Indicator
|  |  |  | 2.1 | Number of national youth and women-led organisations, medical professional associations and civil society organisations in at least six priority countries engaged by Transform Health that are actively campaigning in support of coalition priorities. | 15
|  |  |  | 2.2 | Number of national-level decision-makers in at least six priority countries engaged by Transform Health who have publicly recognised the fundamental role of digital technology and data to achieve UHC. | 2
|  |  |  | 2.4 | Number of states and non-state digital health actors that have demonstrated support for creating a global health data governance framework. | 10 | 1
|  |  |  | 2.5 | Number of countries with effective national or regional governance mechanisms for health data.
|  |  |  | 2.6 | Number of countries that have created/strengthened effective national policies/regulations on health data. | 1
|  |  |  | 2.7 | Number of countries with digital health strategies that prioritise PHC and core principles. | 1
|  |  |  | Output indicators | Indicator
|  |  |  | 3.1 | Number of national campaign platforms established and in operation. | 1
|  |  |  | 3.2 | Pieces of media generated about/by Transform Health. | 5
|  |  |  | 3.3 | Number of individuals participating in global, regional and national campaign activities. | 50
|  |  |  | 3.4 | Number of national and regional policymakers engaged by Transform Health. | 10
|  |  |  | 3.5 | Number of other digital health actors engaged by Transform Health. | 40
|  |  |  | 3.7 | Number of non-government partners (IOs, academia, civil society, foundations, for profit) endorsing global health data governance principles. | 20
|  |  |  | 3.9 | Number of global, regional and national partners that have integrated the call for stronger health data governance into their work. | 5
|  |  |  | 3.10 | Number of high-level champions advocating for stronger global governance of health data. | 2
|  |  |  | 3.12 | Number of national decision-makers and partners engaged by Transform Health on health data governance. | 5
|  |  |  | 3.16 | Number of Transform Health engagements in national policy and budgetting processes. | 1
|  |  |  | 3.17 | Number of national reports produced by Transform Health or partners on the status of national digital health strategies and budgets. | 1
|  |  |  | 3.20 | Number of campaign activities driven by youth, women and marginalised communities. | 5
|  |  |  | 3.21 | Number of youth and women-led partners engaged in national campaign activities. | 10
|  |  |  | 3.22 | Number of skill-sharing and capacity-building activities held to meet needs identified by partners. | 1
|  |  |  | 3.23 | Total number of partners participating in the coalition (by type of organisation and geographic region). | 20

## TAB 3 M&E (hidden)
MONITORING & EVALUATION FRAMEWORK 6 months
STRATEGY & ACTIVITY | OUTPUT | OUTCOME | IMPACT